## Parties
INTERESTED PARTIES
Interested Party | Int / Ext | Reason for Inclusion and needs & expectations
BSI | External | Audit for ISO compliance, issue certifications
Swarco | External | Top tier customer
Colas | External | Top tier customer
Other Direct Customer(s) | External | Purchase our services
Employees | Internal | Directly responsible for delivery of service
Staffing Agencies | External | Provide candidates for hiring - conduct initial vetting of candidates
National Highways | External | Government company charged with operating, maintaining and improving roads
UK Government | External | Strategic direction and investment into UK road network
Subcontractors | External | Provides services for delivery of service
Senior Management | Internal | Has direct responsibility for management of the company
Highways Electrical Registration Scheme | External | Audit for HERS compliance, issue certifications
Road User | External | End user of our services
Emergency Services | External | Road users
Health & Safety Executive (HSE) | External | Accidents and RIDDORs
Environmental Protection Agency (EPA) | External | Emergency spills/contamination
Local Community | External | Enhance positive company image and relations
Neighrbours | External | Engagement with neirbouring properties to ensure no issues
BUPA | External | Prefered health care provider
Tees Medical Services | External | Prefered Occupation Health advisor
Wave Utilities | External | Water utility company
Waste Contractors | External | waste management
Middlesbrough Council | External | Local authority - permits, H&S, environmental, planning
External SHEQ consultant | External | Provides SHEQ consultancy

## Issues
ISSUES OF CONCERN
Ln | Interested Party | Issue of Concern | Bias | Processes Affected | Treatment Method | Record Reference / Notes
1 | BSI | Level of compliance to ISO standards | Mixed | Management Responsibilities | Internal Auditing | See audit records
2 | Direct Customer(s) | May reduce spend | Risk | Service Delivery | Risk Register / FMEA | See Risk Register
3 | Direct Customer(s) | Could be source of referrals to new customers | Opportunity | Service Delivery | Opportunity Register | See Opportunity Register
4 | Direct Customer(s) | If happy, could expand current business | Opportunity | Service Delivery | Opportunity Register | See Opportunity Register
5 | Direct Customer(s) | May require additional services outside of our current scope | Risk | Service Delivery | Risk Register / FMEA | See Risk Register
6 | Employees | Expect to be compensated | Risk | Resource Management | Manage company finances appropriately | Financials (confidential)
7 | Employees | Expect satisfactory equipment, facilities | Risk | Resource Management | Equipment and building maintenance, provision of resources | Maintenance records, management review records
8 | Employees | Require appropriate training | Risk | Resource Management | Training provided, assessed through audits | See training records, audit records
9 | Staffing Agencies | Concerned with reputation of our company as a employer | Risk | Resource Management | Adhere to employment laws, health & safety, contractual obligations, etc | No special actions required
10 | Staffing Agencies | Must provide adequate candidates | Risk | Resource Management | Assess and interview candidates, notify agency of problems | Hiring and training records
11 | Subcontractor | Expect to be paid promptly | Risk | Resource Management | Manage company finances appropriately | Financials (confidential)
12 | Subcontractor | Subcontractor performance impacts on our reputation | Mixed | Resource Management | Subcontractor performance oversight | See management review records
13 | Subcontractor | Have concerns that we may impact on their reputation | Risk | Resource Management | Management Review Activity | See management review records
14 | Senior Management | Company must remain financially healthy | Risk | Management Responsibilities | Manage company finances appropriately | Financials (confidential)
15 | Senior Management | QMS processes must be efficient | Risk | Management Responsibilities | Risk Register / FMEA | See Risk Register
16 | Senior Management | Concerned with growth of company | Opportunity | Management Responsibilities | Management Review Activity | Management review records, financials (confidential)
17 | Senior Management | Company must maintain sufficient staff | Risk | Resource Management | Risk Register / FMEA | See Risk Register
18 | Senior Management | Requires reliable equipment and facilities | Risk | Resource Management | Risk Register / FMEA | See Risk Register
19 | UK Government | Could change strategic investment plant in highways | Mixed | Management Responsibilities | Risk Register / FMEA & Opportunity Register | See Risk & Opportunity Register
20 | National Highways | Projects may be changed | Mixed | Management Responsibilities | Risk Register / FMEA & Opportunity Register | See Risk & Opportunity Register
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54

## Risk Register
RISKS
Ln # | Process | Risk | Probability (of risk occurring) |  | Prob. Rating | Consequence (if risk is encountered) | [5 empty] | Cons. Rating | Risk Factor (Prob x Cons) | Mitigation Plan | Risk Factor after Mitigation | Status
|  |  | Likelihood | Previous Occurrences |  | Potential Loss of the Customer | Potential Inability to Meet Immediate Job Requirements | Potential Risk to Human Health | Potential Violation of Regulations | Impact on Company Reputation | Est. Cost of Correction / Financial Penalty |  |  | (Required for risk factors >=8, suggested for risk factors between 5 and 8)
1 | Service Delivery | Key customers may reduce spend | Somewhat likely to occur | Has never occurred. | 2 | Very High | Minor | None / NA | None / NA | Minimal | > £100,000 | 2.5 | 5 |  |  | CLOSED
2 | Service Delivery | Customers may require additional services outside of our current scope | Unlikely to occur | Has never occurred. | 1.5 | Minor | High | None / NA | None / NA | None | 0 | 1.6667 | 2.5 |  |  | CLOSED
3 | Management Responsibilities | QMS Processes become inefficient | Unlikely to occur | Has never occurred. | 1.5 | None / NA | None / NA | Minor | Possible | Moderate | < £10,000 | 1.8333 | 2.75 |  |  | CLOSED
4 | Resource Management | Company does not maintain sufficient staff | Somewhat likely to occur | Has never occurred. | 2 | Minor | Minor | Moderate | Possible | Moderate | < £10,000 | 2.3333 | 4.6667 |  |  | CLOSED
5 | Resource Management | Company does not have reliable equipment or facilities | Unlikely to occur | Has never occurred. | 1.5 | High | High | High | High | Severe | > £100,000 | 4 | 6 | Conduct all preventative maintenance and investment strategy | 3 | CLOSED
6 | Management Responsibilities | UK Government could change strategic investment plan away from highways | Unlikely to occur | Has not occurred in past 10 years. | 2 | Minor | None / NA | None / NA | None / NA | None | > £500,000 | 1.8333 | 3.6667 |  |  | CLOSED
7 | Management Responsibilities | Highways England may change projects that are planned | Unlikely to occur | Has occurred in past 5 years. | 3 | Minor | None / NA | None / NA | None / NA | None | < £100,000 | 1.5 | 4.5 |  |  | CLOSED
8 | Service Delivery | Introduction of driverless cars and therefore change in highways technology | Very likely to occur | Has never occurred. | 3 | Moderate | Minor | None / NA | None / NA | None | 0 | 1.5 | 4.5 |  |  | CLOSED
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on D4: Chris Paris: This is an estimate of how likely you think the risk is; what is the chance of it happening.
Note on E4: Chris Paris: This is a consideration of whether the risk has already happened; an unlikely risk may still have happened recently, so this helps dial in the Probability number a bit.
Note on G4: Chris Paris: Here the risk is so bad, the customer pulls ALL their orders or work from your company.
Note on H4: Chris Paris: This column reflects the risk impacting on only the immediate job you're working on; not the entire customer contract. This might be for a single order or single delivery.
Note on I4: Chris Paris: This is dependent on the risk: might be harm or injury to your workers in some cases, might be harm to the customer or public in other cases. It depends on each risk.
Note on J4: Chris Paris: This means the risk would cause you to violate some law, statute, regulation, etc.
Note on K4: Chris Paris: This is the potential damage on your "brand" or reputation in the industry, if the risk happens
Note on L4: Chris Paris: This is your estimate of how much $$ this risk will cost you, either to repair something when the risk occurs, or due to some other potential penalty. Higher costs are worse.

## Opp Register
OPPORTUNITIES
Ln # | Process | Opportunity | Probability (of achieving the opportunity) |  | Prob. Rating | Benefit (if opportunity is encountered) | [5 empty] | Ben. Rating | Opp Factor (Prob x Ben) | Opportunity Pursuit Plan (suggested for Opp Factors >=12) May reference external planning document | Post- Implementation Success? | Status
|  |  | Likelihood | Previous Occurrences |  | Potential for New Business | Potential Expansion of Current Business | Potential improvement in satisfying regulations | Potential improvement to internal QMS processes | Improvement to Company Reputation | Potential Cost of Implementation
1 | Service Delivery | Current Direct Customers could be the source of referrals to new customers | Likely to occur | Has never occurred. | 2.5 | Very High | Minor | None / NA | None / NA | Great impact | £0 or N/A | 3.1667 | 7.9167 |  |  | CLOSED
2 | Service Delivery | Current Direct customers, if happy, could expand business with us | Somewhat likely to occur | Has occurred in past year. | 4 | None / NA | Very High | None / NA | None / NA | Moderate impact | £0 or N/A | 2.6667 | 10.6667 |  |  | CLOSED
3 | Management Responsibilities | UK Government could increase strategic investment plant in highways | Unlikely to occur | Has occurred in past 5 years. | 3 | Moderate | Moderate | None / NA | None / NA | Minimal impact | £0 or N/A | 2.5 | 7.5 |  |  | CLOSED
4 | Management Responsibilities | Highways Enfgland may bring forward some projects that may give us some new opportunities | Unlikely to occur | Has occurred in past 10 years. | 2.5 | High | High | None / NA | None / NA | Minimal impact | £0 or N/A | 2.8333 | 7.0833 |  |  | CLOSED
5 | Service Delivery | Technology required to support driverless cars | Very likely to occur | Has never occurred. | 3 | Moderate | High | None / NA | None / NA | Good impact | > £100,000 | 2.5 | 7.5 |  |  | CLOSED
6 | All Processes | Could a training delivery service be created and introduced into the QMS scope | Likely to occur | Has never occurred. | 2.5 | Very High | Moderate | None / NA | None / NA | Minimal impact | > £100,000 | 2.3333 | 5.8333 |  |  | CLOSED
7 | Service Delivery | Driverless cars - more technology in highays | Very likely to occur | Has never occurred. | 3 | High | Moderate | None / NA | None / NA | Minimal impact | > £100,000 | 2.1667 | 6.5 |  |  | CLOSED
8 | Service Delivery | Could the closure of VMSL be a business opportunity to supply signs | Unlikely to occur | Has never occurred. | 1.5 | Very High | High | None / NA | None / NA | Great impact | > £500,000 | 2.8333 | 4.25 |  |  | CLOSED
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on D4: Chris Paris: What is the likelihood that you can obtain this opportunity?
Note on E4: Chris Paris: Have you obtained this opportunity previously?
Note on G4: Chris Paris: Could the opportunity result in you getting new customers or breaking into new markets?
Note on H4: Chris Paris: Could the opportunity result in your current customers increasing their business with you?
Note on I4: Chris Paris: Could this opportunity help you meet laws, statutes, regulations, etc?
Note on K4: Chris Paris: What's the potential for this opportunity to improve your reputation in the industry or your brand?
Note on L4: Chris Paris: How much will this cost to implement? Lower costs are better, in this case.

## Lists (hidden)
OPP RATING RATING: | RISK RATING LIMIT: | Type | Priority | Treatment | Bias | Processes | Likelihood | Occurrences | Potential | Violation | correction | reputation | cost of opp | reputation | score | Success
12 | 8 | External | Emergency | No Action: Accept Risk per Mgmt Decision | Opportunity | All Processes | Cannot occur / not applicable | Has never occurred. | None / NA | None / NA | 0 | None | > £500,000 | No impact / NA | 1 | Opportunity Failed
| RISK CONSIDERATION LIMIT | Internal | High | Risk Register / FMEA Style | Risk | Service Delivery | Unlikely to occur | Has not occurred in past 10 years. | Minor | Possible | < £10,000 | Minimal | > £100,000 | Minimal impact | 2 | Opportunity Abandoned
| 5 |  | Medium | Root Cause Analysis | Neutral | Resource Management | Somewhat likely to occur | Has occurred in past 10 years. | Moderate | Definite | < £100,000 | Moderate | < £100,000 | Moderate impact | 3 | Met some expectations
|  |  | Low | Internal Auditing | Mixed | Measurement, Analysis & Improvement | Likely to occur | Has occurred in past 5 years. | High | High | > £100,000 | Severe | < £10,000 | Good impact | 4 | Met all expectations
|  |  |  | Root Cause Analysis |  | Management Responsibilities | Very likely to occur | Has occurred in past year. | Very High | Legal Risk | > £500,000 | Very severe | £0 or N/A | Great impact | 5 | Exceeded expectations
Corrective Action Request (CAR)
Vendor Auditing
Opportunity Trend Data |  |  |  | Other Auditing
Number Open Improvement Initiatives | 0 |  |  | Management Review Activity
Number Closed Improvement Initiatives | 8 |  |  | Marketing Enhancement
Total Improvement Initiatives to Date | 8 |  |  | Other
Opportunity Failed | 0
Opportunity Abandoned | 0
Met some expectations | 0 | [15 empty] | (Required for risk factors >=
Met all expectations | 0 | [15 empty] | , suggested for risk factors between
Exceeded expectations | 0
(Required for risk factors >=8, suggested for risk factors between 5 and 8)
Risk Trend Data
Total risks processed | 8 | [15 empty] | Opportunity Pursuit Plan (suggested for Opp Factors >=
Total risks requiring action | 0 | [15 empty] | ) May reference external planning document
Total risks suggesting action | 2
Total risks accepted without action | 6 | [15 empty] | Opportunity Pursuit Plan (suggested for Opp Factors >=12) May reference external planning document
Customize these as you like.
The Risk Rating Limit is the minimum risk score which will trigger a MANDATORY mitigation plan.
The Risk Consideration Limit is a score which would trigger a SUGGESTED mitigation plan.
The Opportunity Rating Limit is the minimum score which would require a mandatory "opportunity pursuit plan."