## IMS
INTEGRATED MANAGEMENT SYSTEM
Goal | Objectives | Strategy | Principle Owners | Target Date | Resources | Rational | Status
Integrate all Systems to have one cohesive management systems across the board Integrate the system using Annex SL format and use one accreditation body for all standards. | Develop a new common cohesive Management System for: - 45001:2018 – OSHSM - 14001:2015 – EMS - ISO 9001:2015 – QMS - NHSS8 | Identify and map the strategic (top tier) management system that is applicable to all Standards | L Payne | 2023-06-01 | SHEQ Consultant | Better Communication through having the same systems and information available, cohesive - no mismatch between systems and departments. Integrating systems will have the following benefits: - Meeting all standards’ requirements with one Manual, one set of policies documents and procedures where required. - Increased efficiency and effectiveness. - Reductions in costs associated with audits. - Displays commitment to continuous improvement for the company as a whole. - Presents a clear uniform image of the whole organisation. - Reduces duplication, bureaucracy and maximises resources. - Increases time available to management to implement proactive measures. Improves internal and external communications | Completed
|  | Map out ALL processes within the business and allocate authority, responsibility, and Ownership of those processes, from [top tier] management throughout their departments. | L Payne | 2023-06-01 | SHEQ Consultant |  | Completed
|  | Develop the Management System [from scratch] utilising the best elements existing in current Management system. | L Payne | 2023-06-01 | SHEQ Consultant |  | Completed
| Set up / appoint and Train an Internal Management system Audit team, to impartially assess the effectiveness of the new Integrated Management System. | Train an Internal Audit team with members from all departments. | L Payne | 2023-06-01 | SHEQ Consultant | To ensure impartiality and feedback into the system and continuously improve the business. | Completed
| Set up / appoint and Train an Internal Risk Assessment Team, to reduce risks to the business from internal and external impacts. | Train an Internal risk assessment team to carry out risk assessments | L Payne | 2023-06-01 | SHEQ Consultant | To identify sensible measures to control the risks in workplace minimising business impacts and continuously improve the business and better understand risks facing the business. | Completed
| Promote sharing of HSEQ information between all departments across all business functions. | Integrate HSEQ IMS Manual and IMD Controlled Documentation between all business functions. | L Payne | 2023-06-01 | Digital Transformation Consultancy Various software solutions incluidng Microsoft Sharepoint Airtable Cognito Forms MS Office applications ERP System | Accelerate how work gets done, organise, connect and share critical business information. Reduces the risk of errors – data will not have to be replicated, there is less chance of human errors being made which leads to more accurate information available. Greater productivity – Employee can spend more time on tasks that will help the business grow, rather than having to replicate data and wait for information to be sent to them from other departments. | Completed
Registration to ISO 45001:2018, 14001:2015, ISO 9001:2015 [Including NHSS 8]. Under one UKAS Accredited Body. | Identify additions and sequential changes through Gap Analysis. Have all Systems 45001:2018, 14001:2015, ISO 9001:2015 & NHSS 8 Registered under one Accreditation body. | Continue with transition to an IMS Manual. Introduce IMS controlled documents [IMD]. Implement IMS Policies [IMP]. Audit the system while in progress. | L Payne | 2023-10-01 | Internal audit team SHEQ Consultant | UKAS is the United Kingdom Accreditation Service; they are appointed by the government to be the sole agency authorised to assess the ability and competence of organisations that provide certification. BSI already accredit ISO 9001:2015. Logically BSI should be used to accredit the IMS to 45001:2018, 14001:2015, and NHSS 8. | Completed

## OHAS
OCCUPATIONAL HEALTH & SAFETY
Goal | Objectives | Strategy | Principle Owners | Target Date | Resources | Rational | Status
To provide better awareness and competency to ensure all our employees are informed of their responsibilities | Determine Roles and Responsibilities for all employees and management | Every Manager, supervisor, foreman and worker will be made aware in their Job Descriptions of their Health & Safety roles & responsibilities | L Payne | 2023-06-01 | None | Under section 7 of HASAW 1974 employees have a duty to take reasonable care for the health and safety of themselves and others who may be affected by their acts or omissions whilst at work. This extends to co-operating to enable the employer to fulfil its legal duty. Job descriptions are to define duties, roles & responsibilities. | On-going
| Increase competence and awareness of all employees about Health & Safety across the site | Occupational Health & Safety Training for all managers. | L Ratcliff | 2023-12-01 | IOSH Approved training provider | Train Managers and supervisors within the workplace to provide a thorough understanding of health and safety emphasising the importance of monitoring staff and controls | Completed Refreshers may be required
|  | Basic foundation course Occupational Health & Safety Training for all employees | L Ratcliff | 2023-11-01 | IOSH Approved training provider | Training for Employees to understand their roles and responsibilities in reducing risks and supporting health and safety in the working environment including risk profiling and its contribution to health and safety, incident reporting and emergency procedures. | On-going
| Increased communication across the site | Increase Toolbox Talks | Supervisors | 2023-07-01 | Software including Cognito Forms Airtable | To ensure a quick refresher on a single subject, to bring attention to a relevant health and safety topic, to keep knowledge refreshed | On-going
|  | Targeted feedback regarding employee reports | Supervisors | 2023-10-01 | Software including Cognito Forms Airtable | To encouraging feedback for incident reduction. | On-going
|  | Introduce ROES [Representative of Employee Safety] | L Payne | 2023-07-01 | None | Having elected RoES encourages employee involvement and can make a real and balanced contribution to safety through agreed consultation with employers. | On-going
|  | Introduce an Employee suggestion scheme | H Medcalf | 2023-06-01 | Software including Cognito Forms Airtable | A suggestion scheme motivates employees who undertake tasks to use their experience and expertise, to suggest to management what improvements, they can assist in the development of the safety culture. | On-going
| Train all employees in correct manual handling techniques | Implement training to improve manual handling across site | L Ratcliff | 2023-09-01 | Qualsafe Approved training provider | To assess processes and comply with the MHOR 1992 to avoid the need for hazardous manual handling. | Completed Refreshers may be required
To scrutinise our ways of working to ensure our processes are reinforcing safe working practices | Identify the high-risk processes that will feed into our process reviews | Implement a Risk Assessment Register and Trained risk assessors. | L Payne H Medcalf P Rye | 2023-06-01 | Risk Assessment training provider | To set out the requirements and provide direction in prioritising & collating Health & Safety Risk assessments throughout the Company. | On-going (on schedule)
To continual improvement of our safety management system | Review accident investigations in more detail | Accident Investigation Training to identify root causes | L Payne | 2023-11-01 | Software including Cognito Forms Airtable | To have highly trained workplace investigators of incidents. | Not yet started
| Increased observation and near miss reporting from all departments | Training in Heinrich's triangle theory of accident prevention | L Payne | 2023-12-01 | None | Excelling in safety and have embedded near miss reporting built into the safety culture catching hazards before they cause harm. | Not yet started
| Implement house keeping across departments | Training & understanding of house keeping for all employees. | L Payne | 2023-12-01 | None | Promote a clean working environment to reduce or eliminate work-related injuries to help ensure workplace safety. | Not yet started
| Introduce a planned preventative maintenance | A PPM schedule and register to be introduced using | L Payne | 2023-12-01 | Software including Cognito Forms Airtable | PUWER requires that: all work equipment be maintained in an efficient state. Comply with PUWER and LOLER Regulations. | On-going
| Achieve ISO 45001 certification | Implement IMS System Manual and Audit. | L Payne | 2023-08-01 | SHEQ Consultant | To reduce the risk of injury and ill health, fulfil our moral duty as a responsible employer, Improve health and safety performance. | On-going (on schedule)

## EMS
ENVIRONMENTAL
Goal | Objectives | Strategy | Principle Owners | Target Date | Resources | Rational | Status
To improve Environmental Awareness at all levels of the business with the goal of maintaining our low environmental impact. | Improve awareness of environment related activities by educating employees at all levels of the business utilising Awareness training | Carry out Environmental awareness training, for all employees. schedule training throughout the year | L Payne | 2023-09-01 | SHEQ Consultant | To make employees aware of how their activities, the materials or products they use and create, can harm the environment and to raise awareness of environmental issues and improving the company’s environmental performance, and standardising the training for all employees. | Not yet started
| Evaluate emergency preparedness for accidental spills in the workplace. | Carry out spill response training for those on the spill response team. | L Payne | 2023-09-01 | SHEQ Consultant | To ensure a spill that can be controlled does not become an environmental disaster. To ensure employees know how they should respond to spills of fluids and hazardous chemicals in the workplace, and ensure they have a basic knowledge of what to do and what not to do when encountering a spill. | Not yet started
To improve Environmental impacts | Identify potential environment impacts selected for 2023 create aspects and impacts register | Undertake internal analysis to identify aspects and impacts | L Payne | 2023-12-01 | Software including Cognito Forms Airtable | To determine the Company impacts on the Environment. | Completed
| To improve the environmental footprint of the business. | Encourage electric/hybrid vehicles in Company Car Fleet. | D Bullock | 2023-03-01 | Company Car Fleet | To reduce the overall energy consumption of operations, reduce fuel costs, reduce emissions to atmosphere. | Completed
|  | Deploy LED Lighting into office areas (Balancing Lux Levels/Brightness) with automatic detection sensors to turn on/off when needed | L Payne | 2023-12-01 | LED lighting & sensors |  | Completed
Achieve 14001:2015 Accreditation | To create an EMS capable of: - Identifying and controlling the environmental impact of activities, products and services. - Continually improving environmental performance. | Implement IMS System Manual and Audit. Implement Aspects and impacts Register and update. Monitor and review performance. | L Payne | 2023-08-01 | SHEQ Consultant | To demonstrate that we are controlling our environmental impact and putting in place systems that will not only benefit the environment but will also reduce costs and improve efficiency within the organisation. Cost savings in waste, recycling and consumption, Management of environmental risks, Compliance environmental regulations and increase employee engagement. | Completed

## QMS
QUALITY
Goal | Objectives | Strategy | Principle Owners | Target Date | Resources | Rational | Status
To maintain and improve ISO9001:2015 Quality Management systems and retain accreditation. | Ensure internal audit schedule is current and up to date and the audit function adds value. | Train an Internal Audit team with members from all departments to provide independent objective evidence from the function being audited | L Payne | 2023-07-01 | SHEQ Consultant | Auditors cannot audit their own work/department without having a definite conflict of interest. An internal auditor, or internal audit team, cannot have any operational responsibility for that function to achieve an objective insight. Cross-train employees in different departments to be able to audit another department. | Completed
| Ensure Management Reviews are scheduled, and timings adhered to regardless of who is available. | Set the agenda for the management review. | L Payne | 2023-07-01 | None | To ensure that all quality related functions are reviewed at the highest possible level and so that all levels of management affecting quality are made aware of changes, updates, revisions, verification activities and policies. To establish that the Quality Assurance System is achieving the expected results, continuing to conform to the standard, and functioning in accordance with the established internal operating procedures. To expose irregularities or defects in the System, identify weaknesses and to make recommendations for continual improvement. To review the effectiveness of previous corrective actions including those related to subcontractor and supplier performance. To review the adequacy and suitability of the quality assurance system for current and future operations. To review the finding of internal / external audits and identify any areas of recurring problems. To review reports of non-conformities and evaluate any trends. To review training requirements. Analyse all the above for trends and make appropriate improvements To review any complaints received, identify the cause and recommend corrective action if required, including customer feedback. | Completed
| Close out historical non-conformities and update corrective actions and keep up to date and on top of NCR’s | Continue to use CAR Register | L Payne | 2023-06-01 | None | To ensure the swift closure of non-conformities To ensure Correction i.e. that the nonconformity has been determined and contained. To provide evidence that the corrective action was implemented or is being implemented. And Root Cause Analysis, why it happened in the first place? | Completed