## Log
CAR Log - Rev. 003
|  |  |  | Today's date is | 2023-09-19 | [6 empty] | VERIFICATION ACTIVITIES
CAR # | Date Submitted | Type | Source | Process | Name of Person Submitting CAR | Brief Description | Assigned To | Date Assigned | Requested Action Due Date | Overdue? | Action Complete Date | Immediate Follow-Up Date | Immediate Follow-Up Result | If FAIL, Date Reassigned | Long Term Follow-Up Req'd? | Long Term Follow-Up Date | Long Term Follow-Up Result | If FAIL, New CAR # | Closed? | Days Late
42 | 2017-12-21 | Corrective | External Audit | Management Responsibilities | Lee Payne | The June 2017 Management review failed to review all requirements including; e) the effectriveness of actions taken to address risks and opportunitites | David Bullock | 2017-12-22 | 2018-01-12 | NO | 2018-01-09 | 2018-01-10 | PASS |  | NO | 2008-12-17 | PASS |  | YES | -3
43 | 2017-12-21 | Corrective | External Audit | Measurement, Analysis & Improvement | Lee Payne | The 2017 Audit Plan and the 207 Internal audit conducted in October (Audit #4) failed to include Risks & Opportunities (6.1), and the needs & expectations of Interested Parties (4.2). | David Bullock | 2017-12-22 | 2018-01-12 | NO | 2018-01-09 | 2018-01-10 | PASS |  | NO |  |  |  | YES | -3
44 | 2017-12-21 | Corrective | External Audit | Resource Management | Lee Payne | Unable to locate calibration records for two assets listed on the calibration equipment register: - Asset # MM001 : Fluke 123 Multi Meter - Asset # MTE001 : Fluke 1567 Multifunctional Tester | David Bullock | 2017-12-22 | 2018-01-12 | NO | 2018-01-09 | 2018-01-10 | PASS |  | NO |  |  |  | YES | -3
45 | 2018-04-03 | Corrective | Other | Service Delivery | Dan McCann | We do not currently have a formal complaints procedure to follow for internal and external customers. | Lee Payne | 2018-04-09 | 2018-04-23 | NO | 2018-04-12 | 2018-04-16 | PASS |  | NO | 2008-12-17 | PASS |  | YES | -11 | YES
46 | 2018-04-03 | Corrective | Internal Audit | Service Delivery | Dave Rodwell | Following the testing of a work instruction it showed that a MEWP pre-use check was missing for one day. A MEWP pre-use check should be conducted and recorded each time a MEWP is used according to procedure QMD 015. | Lee Ratcliff | 2018-04-04 | 2018-04-23 | NO | 2018-04-17 | 2018-04-18 | PASS |  | NO |  |  |  | YES | -6 | YES
47 | 2018-04-03 | Corrective | Internal Audit | Service Delivery | Dave Rodwell | Following the testing of a work instruction it was shown that pre-start briefings were not recorded as stated in the QMD 016 procedure | Lee Ratcliff | 2018-04-04 | 2018-04-23 | NO | 2018-04-17 | 2018-04-18 | PASS |  | NO |  |  |  | YES | -6 | YES
48 | 2018-05-17 | OFI | Management Review Action Item | Resource Management | Lee Payne | Build a Test Area within the unit to aid electrical testing | Lee Ratcliff | 2018-05-18 | 2018-09-18 | NO | 2018-05-25 | 2018-07-09 | PASS |  | NO |  |  |  | YES | -116
49 | 2018-05-17 | OFI | Management Review Action Item | Resource Management | Lee Payne | A Supervisor to attend the CITB SMSTS course to offer us the ability to provide a Site Manager should a client require us to do so moving forward. | Daniel McCann | 2018-05-18 | 2018-09-18 | NO | 2018-07-09 | 2018-07-16 | PASS |  | NO |  |  |  | YES | -71
50 | 2018-05-17 | OFI | Management Review Action Item | Resource Management | Lee Payne | Though not essential, we still need to provide training for Forklift use and also IOSH working safely for those staff identified. | Daniel McCann | 2018-05-18 | 2022-12-31 | NO | 2022-10-09 | 2022-10-09 | PASS |  | NO |  |  |  | YES | -83
51 | 2018-05-17 | Preventive | Management Review Action Item | Management Responsibilities | Lee Payne | Implement the transition to ISO 9001:2015 standard goal needs to be removed or amended from the Quality Objectives as it has been fully completed. | David Bullock | 2018-05-18 | 2018-05-25 | NO | 2018-05-21 | 2018-05-21 | PASS |  | NO |  |  |  | YES | -4
52 | 2018-07-12 | Preventive | Management Review Action Item | Resource Management | Lee Payne | Further review of van needs for the next 1-2 years required to decide on acquisition plans for the remainder of this year. | Lee Payne | 2018-07-13 | 2018-09-30 | NO | 2018-08-28 | 2018-08-28 | PASS |  | NO |  |  |  | YES | -33
53 | 2018-12-20 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | Remove quality objectives from ISO QMS Manual and update in each MRM. Then create a Continuous Improvement Objectives log to see what has been done to achieve these objectives. The Continuos Improvement Log can then be reviewed as part of the MRM. | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-18 | 2019-01-18 | PASS |  | NO |  |  |  | YES | -13
54 | 2018-12-20 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | Create a Continuous Improvement Log | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-17 | 2019-01-17 | PASS |  | NO |  |  |  | YES | -14
55 | 2018-12-20 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | Update the Management Review agenda and procedure as a result of the Continuos Improvement Log | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-17 | 2019-01-17 | PASS |  | NO |  |  |  | YES | -14
56 | 2018-12-20 | OFI | Management Review Action Item | Measurement, Analysis & Improvement | Lee Payne | Change to Internal Audit. Add which procedure - including the version, covers which clause in Appendix B of QMS Manual - Then at audit, check if the versions or standards have changed. If not, all procedures are OK to pass. - Then use the remainder of the audit to review the reality against the documented procedure using an Audit Checklist. | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-18 | 2019-01-18 | PASS |  | NO |  |  |  | YES | -13
57 | 2018-12-20 | OFI | Management Review Action Item | Measurement, Analysis & Improvement | Lee Payne | Internal Audit Some processes could be audited more frequent / less frequent to ensure quality objectives are met. Suggested the following frequency: - Service Delivery - Annually - Resource Management - Annually - Measurement, analysis & improvement - Every 3 years - Management Reponsibility - Every 3 years - Review of procedures versions (as above) - Annually | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-20 | 2019-01-20 | PASS |  | NO |  |  |  | YES | -11
58 | 2018-12-20 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | State procedure references on Appendix A of the QMS Manual | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-20 | 2019-01-20 | PASS |  | NO |  |  |  | YES | -11
59 | 2018-12-20 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | Change 11.2 in QMS Manual from: • recording customer complaints using the document QMD 025 – Complaints. • obtain customer scorecards from certain customers • submittal of customer satisfaction surveys to: • recording customer complaints using the document QMD 025 – Complaints. • regular feedback from clients, both written and verbal which is to be discussed at Management Reviews | Lee Payne | 2019-12-20 | 2019-01-31 | NO | 2019-01-20 | 2019-01-20 | PASS |  | NO |  |  |  | YES | -11
60 | 2019-03-26 | Corrective | Internal Audit | Service Delivery | Dave Rodwell | Following the testing of a work instruction it was shown that pre-start briefings were not recorded as stated in the QMD 016 procedure | Lee Ratcliff | 2019-03-26 | 2019-04-26 | NO | 2019-04-02 | 2019-04-02 | PASS |  | NO |  |  |  | YES | -24
61 | 2019-08-06 | OFI | Management Review Action Item | Resource Management | Lee Payne | Equip Senior Management with iPad, keyboard and Pencil to improve mobile working environmen | Lee Payne | 2019-08-06 | 2019-10-31 | NO | 2019-08-24 | 2019-08-24 | PASS |  | NO |  |  |  | YES | -68
62 | 2019-08-06 | OFI | Management Review Action Item | Resource Management | Lee Payne | New office desk configuration to be introduced to aid collaborative working | Lee Payne | 2019-08-06 | 2019-10-31 | NO | 2019-08-13 | 2019-08-13 | PASS |  | NO |  |  |  | YES | -79
63 | 2019-08-06 | OFI | Management Review Action Item | Resource Management | Lee Payne | It has become a contractual requirement on some schemes lately that FORS Bronze accreditation is required for companies that hold an operator license. To enable for us to win new contracts and to improve the quality performance of our fleet operation, it is agreed that we are to gain FORS Bronze accreditation as soon as possible. | Lee Payne | 2019-08-06 | 2019-10-31 | NO | 2019-09-05 | 2019-09-05 | PASS |  | NO |  |  |  | YES | -56
64 | 2019-08-06 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | With the small nature of the team and the frequent informal meetings, it has been decided that a in-depth Management Review Meeting should be held every 6 months. This will provide the meeting with more meaning moving forward. | Lee Payne | 2019-08-06 | 2019-08-31 | NO | 2019-08-20 | 2019-08-20 | PASS |  | NO |  |  |  | YES | -11
65 | 2021-06-28 | Corrective | Management Review Action Item | Service Delivery | Lee Payne | QMD 011 - Customer enquiry / quotation procedure. Due to new customer requirements, the procedure in reality has now changed | Lee Payne | 2021-06-28 | 2021-07-28 | NO | 2021-07-12 | 2021-07-12 | PASS |  | NO |  |  |  | YES | -16
66 | 2021-06-28 | Preventive | Management Review Action Item | Service Delivery | Lee Payne | QMD 012 - Forecasting / Planning procedure. We no longer believe we should use the shared calendar and just use the warboard as this is what we all use in reality. Therefore the procedure needs updating. | Lee Payne | 2021-06-28 | 2021-07-28 | NO | 2021-07-12 | 2021-07-12 | PASS |  | NO |  |  |  | YES | -16
67 | 2021-06-28 | Preventive | Management Review Action Item | Service Delivery | Lee Payne | QMD 018 - Control Activities procedure. The existing procedure is seemingly over complicated and not effective. As a result, procedure needs refining. | Lee Payne | 2021-06-28 | 2021-07-28 | NO | 2021-07-12 | 2021-07-12 | PASS |  | NO |  |  |  | YES | -16
68 | 2021-06-28 | Preventive | Management Review Action Item | Service Delivery | Lee Payne | QMP 001 - Due to changes, in QMD 011, 012 and 018, this process overview will need updating. | Lee Payne | 2021-06-28 | 2021-07-28 | NO | 2021-07-12 | 2021-07-12 | PASS |  | NO |  |  |  | YES | -16
69 | 2021-11-30 | OFI | Internal Audit | Resource Management | Dave Rodwell | QMD 021 – Control of Third Party Property. Not a significant amount of third party property present. Aspects of the process assessed and confirmed. Consider reviewing procedure as this area of the business is expected to grow | Lee Payne | 2021-11-30 | 2022-12-31 | NO | 2022-12-20 | 2022-12-20 | PASS |  | NO |  |  |  | YES | -11
70 | 2022-06-27 | OFI | Management Review Action Item | Service Delivery | Lee Payne | As we are getting more and more virtual meeting requests, we need a solution to host calls within the office. It was discussed that the old office be converted into a new webconferencing meeting room. | Lee Payne | 2022-06-27 | 2022-12-31 | NO | 2022-07-26 | 2022-07-26 | PASS |  | NO |  |  |  | YES | -158
71 | 2022-11-17 | Corrective | External Audit | Resource Management | Lee Payne | Processes associated with the provision and availability of assets required to undertake planed works could not be demonstrated as being fully effective. 1. Weekly FASSI Crane Checks on SCANIA R500 had not been completed within the last three weeks despite evidence indicating the asset had been used. 2. Two torque wrenches Wera Click-Torque C3 (Serial #'s VE15370 & VG16872) had exceeded their 12 month operational life and had not been replaced (or calibrated) | Lee Payne | 2022-11-17 | 2022-12-02 | NO | 2022-12-01 | 2022-12-01 | PASS |  | NO |  |  |  | YES | -1
72 | 2022-12-19 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | Due to the change in strategic direction of the business to begin manufacturing variable message signs, and in order to supply National Highways, the company will need accreditation to ISO 45001 and 14001 in addition to its ISO 9001. | Lee Payne | 2022-12-20 | 2023-03-31 | NO | 2023-01-30 | 2023-01-30 | PASS |  | NO |  |  |  | YES | -60
73 | 2022-12-19 | OFI | Management Review Action Item | Management Responsibilities | Lee Payne | As we are moving to ISO 45001 and 14001 accreditation in addition to ISO 9001, it makes sense for the management system to be changed to an Integrated Management System | Lee Payne | 2022-12-20 | 2023-03-31 | NO | 2023-01-30 | 2023-01-30 | PASS |  | NO |  |  |  | YES | -60
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[14 empty] | 2010-09-30 | [5 empty] | 0
0
0
0
0
0
[14 empty] | T. Battelene | [5 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Report
CAR TREND REPORT
|  |  | Apply date filter: | 36 | months
EXECUTIVE SUMMARY | [5 empty] | Process | Total | All To Date |  |  | Last 36 Months
[8 empty] | Corrective | Preventive | OFI | Corrective | Preventive | OFI
2023-09-19 | All To Date | Last 36 Months |  |  |  | Service Delivery | 9 | 5 | 3 | 1 | 1 | 3 | 1
Total CARs filed | 32 | 9 |  |  |  | Resource Management | 10 | 0 | 0 | 0 | 1 | 0 | 1
Average CARs per month | 0.47059 | 0.25 |  |  |  | Measurement, Analysis & Improvement | 3 | 2 | 1 | 7 | 0 | 0 | 0
[6 empty] | Management Responsibilities | 10 | 0 | 0 | 0 | 0 | 0 | 2
CARs Closed | 32 | 9 |  |  |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0
CARs Open | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 1 | 1 | 8 | 0 | 0 | 0
CARs awaiting assignment | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARs overdue for action | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARs that were processed late | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARs awaiting verification | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARs failed verification | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARs passed verification | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer-Related CARs | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Avg Customer CARs per Month | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total employee preventive action CARs | 5 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total employee suggestions for improvement | 18 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total ALL employee proactive CARs | 23 | 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Avg employee proactive action CARs per month | 0.33824 | 0.10294 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTALS | 32 | 9 | 5 | 18 | 2 | 3 | 4
This sheet is NOT protected, so
be careful when copying and pasting data into your reports, or you may break the formulas or links.

## Data
SETUP AND CALCULATIONS |  |  |  | EDITING THIS SHEET MAY BREAK THE WORKBOOK! |  |  |  | Filename = | 1 - CAR Log.xlsx
| Today is: | 2023-09-19 | NOTE: set date range with drop down in Report tab
| Form name to use: | CAR |  |  | Calc. Date: | 2020-09-19
[10 empty] | DATA BY PROCESS | ALL TO DATE |  |  |  | DATE FILTERED |  |  | DATA BY SOURCE | ALL TO DATE |  |  |  | DATE FILTERED
| Type | ALL TO DATE | DATE FILTERED |  |  |  | EXECUTIVE SUMMARY | ALL TO DATE | DATE FILTERED | Process | TOTAL | Corrective | Preventive | OFI | Corrective | Preventive | OFI | Source | TOTAL | Corrective | Preventive | OFI | TOTAL | Corrective | Preventive | OFI
| Corrective | 9 | 2 |  |  |  | Report Start Date | 2017-12-21 | 2020-09-19 | Service Delivery | 9 | 5 | 3 | 1 | 1 | 3 | 1 | Employee Feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Preventive | 5 | 3 |  |  |  | Total Months of Report | 68 | 36 | Resource Management | 10 | 0 | 0 | 0 | 1 | 0 | 1 | Customer Feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL TO DATE |  |  |  | ALL TO DATE |  |  |  | ALL TO DATE |  |  |  | DATE FILTERED |  |  |  |  | DATE FILTERED |  |  |  |  | DATE FILTERED |  |  |  |  | ALL TO DATE |  |  |  | ALL TO DATE |  |  |  | ALL TO DATE |  |  |  | DATE FILTERED |  |  |  |  | DATE FILTERED |  |  |  |  | DATE FILTERED
| OFI | 18 | 4 |  |  |  | Total CARs filed | 32 | 9 | Measurement, Analysis & Improvement | 3 | 2 | 1 | 7 | 0 | 0 | 0 | Supplier / Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ANALYSIS BY SOURCE - CORRECTIVE |  |  |  | ANALYSIS BY SOURCE - PREVENTIVE |  |  |  | ANALYSIS BY SOURCE - OFIs |  |  |  | ANALYSIS BY SOURCE - CORRECTIVE |  |  |  |  | ANALYSIS BY SOURCE - PREVENTIVE |  |  |  |  | ANALYSIS BY SOURCE - OFIs |  |  |  |  | ANALYSIS BY PROCESS - CORRECTIVE |  |  |  | ANALYSIS BY PROCESS - PREVENTIVE |  |  |  | ANALYSIS BY PROCESS - OFIs |  |  |  | ANALYSIS BY PROCESS - CORRECTIVE |  |  |  |  | ANALYSIS BY PROCESS - PREVENTIVE |  |  |  |  | ANALYSIS BY PROCESS - OFIs
| TOTAL | 32 | 9 |  |  |  | Average CARs per month | 0.47059 | 0.25 | Management Responsibilities | 10 | 0 | 0 | 0 | 0 | 0 | 2 | Internal Audit | 4 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Employee Feedback | Type | Source | Result | Employee Feedback | Type | Source | Result | Employee Feedback | Type | Source | Result | Employee Feedback | Date Submitted | Type | Source | Result | Employee Feedback | Date Submitted | Type | Source | Result | Employee Feedback | Date Submitted | Type | Source | Result | Service Delivery | Type | Process | Result | Service Delivery | Type | Process | Result | Service Delivery | Type | Process | Result | Service Delivery | Date Submitted | Type | Process | Result | Service Delivery | Date Submitted | Type | Process | Result | Service Delivery | Date Submitted | Type | Process | Result
| Error checking |  | 100% | [6 empty] | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | External Audit | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 |  | Corrective | Employee Feedback | 0 |  | Preventive | Employee Feedback | 0 |  | OFI | Employee Feedback | 0 |  | >=44093 | Corrective | Employee Feedback | 0 |  | >=44093 | Preventive | Employee Feedback | 0 |  | >=44093 | OFI | Employee Feedback | 0 |  | Corrective | Service Delivery | 5 |  | Preventive | Service Delivery | 3 |  | OFI | Service Delivery | 1 |  | >=44093 | Corrective | Service Delivery | 1 |  | >=44093 | Preventive | Service Delivery | 3 |  | >=44093 | OFI | Service Delivery | 1
[7 empty] | CARs Closed | 32 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Management Review Action Item | 23 | 1 | 5 | 17 | 7 | 1 | 3 | 3 | Customer Feedback | Type | Source |  | Customer Feedback | Type | Source |  | Customer Feedback | Type | Source |  | Customer Feedback | Date Submitted | Type | Source |  | Customer Feedback | Date Submitted | Type | Source | Result | Customer Feedback | Date Submitted | Type | Source | Result | Resource Management | Type | Process |  | Resource Management | Type | Process |  | Resource Management | Type | Process |  | Resource Management | Date Submitted | Type | Process | Result | Resource Management | Date Submitted | Type | Process | Result | Resource Management | Date Submitted | Type | Process | Result
| Date Filter: | Calc Date | Total CARs |  |  |  | CARs Open | 0 | 0 | 0 | 0 | 1 | 1 | 8 | 0 | 0 | 0 | Other | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Corrective | Customer Feedback | 0 |  | Preventive | Customer Feedback | 0 |  | OFI | Customer Feedback | 0 |  | >=44093 | Corrective | Customer Feedback | 0 |  | >=44093 | Preventive | Customer Feedback | 0 |  | >=44093 | OFI | Customer Feedback | 0 |  | Corrective | Resource Management | 2 |  | Preventive | Resource Management | 1 |  | OFI | Resource Management | 7 |  | >=44093 | Corrective | Resource Management | 1 |  | >=44093 | Preventive | Resource Management | 0 |  | >=44093 | OFI | Resource Management | 1
| 6 | 2023-03-19 | 0 |  |  |  |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TOTALS | 32 | 9 | 5 | 18 | 9 | 2 | 3 | 4 | Supplier / Subcontractor | Type | Source |  | Supplier / Subcontractor | Type | Source |  | Supplier / Subcontractor | Type | Source |  | Supplier / Subcontractor | Date Submitted | Type | Source |  | Supplier / Subcontractor | Date Submitted | Type | Source | Result | Supplier / Subcontractor | Date Submitted | Type | Source | Result | Measurement, Analysis & Improvement | Type | Process |  | Measurement, Analysis & Improvement | Type | Process |  | Measurement, Analysis & Improvement | Type | Process |  | Measurement, Analysis & Improvement | Date Submitted | Type | Process | Result | Measurement, Analysis & Improvement | Date Submitted | Type | Process | Result | Measurement, Analysis & Improvement | Date Submitted | Type | Process | Result
| 12 | 2022-09-19 | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Error checking | 100% | 100% |  |  |  | 100% |  |  |  | Corrective | Supplier / Subcontractor | 0 |  | Preventive | Supplier / Subcontractor | 0 |  | OFI | Supplier / Subcontractor | 0 |  | >=44093 | Corrective | Supplier / Subcontractor | 0 |  | >=44093 | Preventive | Supplier / Subcontractor | 0 |  | >=44093 | OFI | Supplier / Subcontractor | 0 |  | Corrective | Measurement, Analysis & Improvement | 1 |  | Preventive | Measurement, Analysis & Improvement | 0 |  | OFI | Measurement, Analysis & Improvement | 2 |  | >=44093 | Corrective | Measurement, Analysis & Improvement | 0 |  | >=44093 | Preventive | Measurement, Analysis & Improvement | 0 |  | >=44093 | OFI | Measurement, Analysis & Improvement | 0
| 24 | 2021-09-19 | 5 |  |  |  | CARs awaiting assignment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Internal Audit | Type | Source |  | Internal Audit | Type | Source |  | Internal Audit | Type | Source |  | Internal Audit | Date Submitted | Type | Source |  | Internal Audit | Date Submitted | Type | Source | Result | Internal Audit | Date Submitted | Type | Source | Result | Management Responsibilities | Type | Process |  | Management Responsibilities | Type | Process |  | Management Responsibilities | Type | Process |  | Management Responsibilities | Date Submitted | Type | Process | Result | Management Responsibilities | Date Submitted | Type | Process | Result | Management Responsibilities | Date Submitted | Type | Process | Result
| 36 | 2020-09-19 | 9 |  |  |  | CARs overdue for action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Corrective | Internal Audit | 3 |  | Preventive | Internal Audit | 0 |  | OFI | Internal Audit | 1 |  | >=44093 | Corrective | Internal Audit | 0 |  | >=44093 | Preventive | Internal Audit | 0 |  | >=44093 | OFI | Internal Audit | 1 |  | Corrective | Management Responsibilities | 1 |  | Preventive | Management Responsibilities | 1 |  | OFI | Management Responsibilities | 8 |  | >=44093 | Corrective | Management Responsibilities | 0 |  | >=44093 | Preventive | Management Responsibilities | 0 |  | >=44093 | OFI | Management Responsibilities | 2
[7 empty] | CARs that were processed late | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | External Audit | Type | Source |  | External Audit | Type | Source |  | External Audit | Type | Source |  | External Audit | Date Submitted | Type | Source |  | External Audit | Date Submitted | Type | Source | Result | External Audit | Date Submitted | Type | Source | Result | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Chart Text | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Corrective | External Audit | 4 |  | Preventive | External Audit | 0 |  | OFI | External Audit | 0 |  | >=44093 | Corrective | External Audit | 1 |  | >=44093 | Preventive | External Audit | 0 |  | >=44093 | OFI | External Audit | 0 |  | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
| All to Date | [5 empty] | CARs awaiting verification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Management Review Action Item | Type | Source |  | Management Review Action Item | Type | Source |  | Management Review Action Item | Type | Source |  | Management Review Action Item | Date Submitted | Type | Source |  | Management Review Action Item | Date Submitted | Type | Source | Result | Management Review Action Item | Date Submitted | Type | Source | Result | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Last 36 Months | [5 empty] | CARs failed verification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Corrective | Management Review Action Item | 1 |  | Preventive | Management Review Action Item | 5 |  | OFI | Management Review Action Item | 17 |  | >=44093 | Corrective | Management Review Action Item | 1 |  | >=44093 | Preventive | Management Review Action Item | 3 |  | >=44093 | OFI | Management Review Action Item | 3 |  | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
| Corrective Actions - By Reporting Source | [5 empty] | CARs passed verification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Other | Type | Source |  | Other | Type | Source |  | Other | Type | Source |  | Other | Date Submitted | Type | Source |  | Other | Date Submitted | Type | Source | Result | Other | Date Submitted | Type | Source | Result | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Preventive Actions - By Reporting Source | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Corrective | Other | 1 |  | Preventive | Other | 0 |  | OFI | Other | 0 |  | >=44093 | Corrective | Other | 0 |  | >=44093 | Preventive | Other | 0 |  | >=44093 | OFI | Other | 0 |  | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
| Suggestions - By Reporting Source | [5 empty] | Total Customer-Related CARs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | TOTALS |  |  | 9 | TOTALS |  |  | 5 | TOTALS |  |  | 18 | TOTALS |  |  |  | 2 | TOTALS |  |  |  | 3 | TOTAL |  |  |  | 4 | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Corrective Actions - By Process | [5 empty] | Avg Customer CARs per Month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | Error Checking |  |  | OK | Error Checking |  |  | OK | Error Checking |  |  | OK | Error Checking |  |  |  | 100% | Error Checking |  |  |  | 100% | Error Checking |  |  |  | 100% |  | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
| Preventive Actions - By Process | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Suggestions - By Process | [5 empty] | Total employee preventive action CARs | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
| Breakdown of CARs by Type | [5 empty] | Total employee suggestions for improvement | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
| Breakdown of CARs by Source | [5 empty] | Total ALL employee proactive CARs | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[7 empty] | Avg employee proactive action CARs per month | 0.33824 | 0.10294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[7 empty] | Total Late | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[7 empty] | Total Days Late | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[7 empty] | Average Days Late | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[7 empty] | Most Days Late | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[10 empty] | TOTALS | 32 | 9 | 5 | 18 | 2 | 3 | 4 | [37 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[10 empty] | Error checking | 100% | 100% |  |  | 100% | [38 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Type | Process |  | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result | 0 | Date Submitted | Type | Process | Result
[55 empty] | Corrective | 0 | 0 |  | Preventive | 0 | 0 |  | OFI | 0 | 0 |  | >=44093 | Corrective | 0 | 0 |  | >=44093 | Preventive | 0 | 0 |  | >=44093 | OFI | 0 | 0
[54 empty] | TOTAL |  |  | 9 | TOTAL |  |  | 5 | TOTAL |  |  | 18 | TOTAL |  |  |  | 2 | TOTAL |  |  |  | 3 | TOTAL |  |  |  | 4
[54 empty] | Error Checking |  |  | 100% | Error Checking |  |  | 100% | Error Checking |  |  | 100% | Error Checking |  |  |  | 100% | Error Checking |  |  |  | 100% | Error Checking |  |  |  | 100%

## CustomisationTab (hidden)
STEP 1: Enter the abbreviated name of your company's Corrective Action form below.
CAR
STEP 2: Enter the list of your processes here, up to 50.
Service Delivery | Erase any extra entries you don't need.
Resource Management
Measurement, Analysis & Improvement
Management Responsibilities