## Setup
List your processes here: | Enter full name of CAR form here | Corrective Action Request
Service Delivery Processes |  | For example, "Corrective Action Request"
Resource Management Processes | Enter abbreviated name of your CAR form here
Measurement, Analysis & Improvement Processes
Management Responsibility Processes |  | CAR
For example, "CAR"
Enter name or title of CAR Administrator here
Lee Payne
For example, "John Smith"

## CAR Form
| Corrective Action Request (CAR) - Rev 002 | [6 empty] | CAR # | This form is protected. Please do not modify. To unlock, go to REVIEW -> UNPROTECT.
71
0
Type Check one
Name:
Date:
Source Check one
Process Check one | Service Delivery Processes |  | Resource Management Processes |  |  |  | Measurement, Analysis & Improvement Processes
| Management Responsibility Processes |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
0
Priority Check One
Describe the issue or problem in detail.
Processes associated with the provision and availability of assets required to undertake planed works could not be demonstrated as being fully effective. 1. Weekly FASSI Crane Checks on SCANIA R500 had not been completed within the last three weeks despite evidence indicating the asset had been used. 2. Two torque wrenches Wera Click-Torque C3 (Serial #'s VE15370 & VG16872) had exceeded their 12 month operational life and had not been replaced (or calibrated)
Stop here. Submit CAR to Lee Payne
CAR Assigned to: | Lee Payne |  |  | Date Assigned: | 2022-11-17 |  | Respond by: | 2022-12-02
To be completed by the Assignee.
Root Cause of Problem: (Required for all corrective and preventive issues; optional for suggestions for improvement.)
Weekly FASSI Crane checks had not been completed due to confusion surrounding the need to be carried out as weekly inspections were also being carried out. The torque wrenches had passed their 12 month operational life by 6 days and had not been placed out of service due to the current system not sending a reminder.
Action Plan: (Actions taken to eliminate root cause, resolve issue and prevent recurrence.)
FASSI weekly crane checks removed for maintenance plan and weekly inspections are only to be used. 2no Torque wrenches removed immediately from service and calibration log updated. A new Maintenance System for equipment to be introduced which sends email reminders when dates are approaching for calibration, LOLERS or any other key dates. A new Workshop Manager has recently been recruited who will oversee all preventative maintenance of all equipment and plant.
Date Action Completed: | 2022-12-01 |  |  |  | Name: | Lee Payne
Stop here. Return CAR to Lee Payne
CAR Effectiveness verified by: |  | Lee Payne |  |  | Date: | 2022-12-01
Result:
Notes and justification: | CAP submitted to BSI
Corrective Action (existing issue)
Preventive Action (potential issue)
Opportunity for Improvement / Suggestion
Employee Feedback
External Audit Finding
Other:
Customer Feedback
Internal Audit Finding
Supplier / Subcontractor Feedback
Management Review Action Item
Other:
Low
Medium
High
Urgent / Critical
Leave blank - will be entered after logging.
Select "CORRECTIVE" if the issue reflects an existing problem.
Select "PREVENTIVE" if the issue reflects a potential problem.
Select "SUGGESTION" if the problem is an opportunity for improvement
Select the SOURCE of the issue -- this is who reported it initially, even if the CAR form itself is being completed by an employee.
Select the PROCESS for which the problem is likely to have occurred:
Select the PRIORITY for the issue being reported:
LOW: Respond as availability allows; may extend deadline with permission of CAR Administrator.
MEDIUM: Respond as soon as feasible; deadline established, but may be interrupted by higher priority activities.
HIGH: Respond by established deadline, which may interrupt other staff working low or medium priority activities.
URGENT / CRITICAL: Respond immediately with sustained effort using all available resources until resolved. Company at legal or other compliance risk.
PASS
FAIL: Returned for Further Processing
Conduct a ROOT CAUSE ANALYSIS. This is an exercise to determine the origin (root cause) of the problem. Consider using the "Five Why" method, by asking "Why did this happen?" and then repeating this five times, in response to each previous answer. Root causes are MANDATORY for corrective and preventive acitons, but optional for OFIs/Suggestions.
Define the ACTION PLAN which will aim to eliminate the root cause, thus correcting or preventing the problem. This plan may be updated as it progresses. If you need more time to complete the plan, request an extension from the CAR Administrator.